## Dashboard
ID | Task Name | Subtask | Estimated Date | Estimated Time | Actual Date | Actual Time | Additional Information | Status | Resource
1 | Creating remote registory | Create a repository | 28/09/21 | 1 h | 28/09/21 | 5 min | repo name: photonic_device | Done | Navodika
|  | Create a project and automate | 28/09/21 | 1 h | 28/09/21 | 10 min | project name: phase_modulator, polarization_modulator, Amplitude_modulator Columns: Backlog, Todo, Ongoing, Done | Done | Navodika
| Optical Phase Modulator | Bit stream generator | 28/09/21 |  | 29/09/21 | 5 min | No need to be random | Done | Navodika
|  | Transverse phase modulator | 28/09/21 |  | 29/09/21 | 1 h | Lithium Niobate medium Release v1.0.0 | Ongoing | Navodika
|  | Longitudinal phase modulator | 28/09/21 |  |  |  |  | Todo | Navodika
| Optical Polarization Modulator | Transverse polarization modulator | 30/09/21 |  | 30/09/21 |  | Lithium Niobate medium Release v2.0.0 | Ongoing | Navodika
| Optical Amplitude Modulator | Longitudinal polarization modulator | 30/09/21 |  | 30/09/21 | 1 h | GaAs polarization modulator Release v3.0.0 | Ongoing | Navodika
𝐿𝑖𝑁𝑂_3
𝐿𝑖𝑁𝑂_3

## Variables
Status | Resource
Todo | Navodika
Ongoing
Done